## Sheet1
<Group Number> - <Paper Name>
Name | Role in the Group | What is done since last update | What will be done | Challenges | Comments
Alex | Data-Miner | *Collect date-time stamps for both issues and commits for the mongo project and as a back up, the django project, as well as the contributors credited with each commit for later calculation of ownership * Will report to us about possible noise, empty commits and missing data. | * Calculate LOC per Commit per Component per Author for fourth set of Four Months * Calculate Ownership of Component * | * * *
Ian Eilopoulos | Data Miner/ Quality Checker/Power-point master | * Identify components in mongo code * Find a way to link commits to components | * Calculate LOC per Commit per Component per Author for second set of Months * Calculate Ownership of Component * Create Powerpoint slide for final report | * * *
Kelby Mah | Data-Miner | * Find Reports + Studies +Papers that could be used in reference to finding season software productivity trends | * Calculate LOC per Commit per Component per Author for third set of Four Months * Calculate Ownership of Component * | * * *
Kevin Giang | Data-Miner | * Identify components in mongo code * Find a way to link commits to components | * Calculate LOC per Commit per Component per Author for last set of Four Months * Calculate Ownership of Component *Calculate Issues vs ownership per month *Calculate Issues vs ownership in general | * * *
Kevin Tran | Data-Miner | * Find Reports + Studies +Papers that could be used in reference to finding season software productivity trends | * Calculate LOC per Commit per Component per Author for fifth set of Four Months * Calculate Ownership of Component * | * * *
Irene Mayor | Group Organizer/Quality Checker/Data Miner | * Identify components in mongo code * Find a way to link commits to components | * Calculate LOC per Commit per Component per Author for first set of Four Months * Calculate Ownership of Component | *Reading the code took a bit of effort to figure out how it organized itself into parts before settling onto directories as components *Creating the script to link commits to components took some work. There's still a lot of work to do in excel